## Plan & Effort
Foot Scan → Custom Insole — Plan & Effort Estimation
One sheet. Effort in hours (8 h/day); time in calendar weeks. Milestone 1 = 3 weeks (full pipeline), Milestone 2 = 2 weeks (refinement).
Milestone | Week | Work Item | Description | Effort (hours)
Milestone 1 — Full Production Pipeline (3 weeks)
M1 | W1 | Capture protocol + in-app guidance | Enforce weight-bearing, ankle framing, scale marker/LiDAR, coverage, lighting; real-time capture hints. | 24
M1 | W1 | Ingestion + video keyframes | Accept image batches and video; extract sharpest/most-diverse keyframes; normalise formats (HEIC). | 16
M1 | W1 | Image quality gate (Agent 1) | Blur, exposure, foot presence, angle coverage/diversity, resolution, marker presence; reject reasons. | 24
M1 | W1 | Foot localisation (vision-LLM crop) | Vision model locates the foot per frame; crop to it (keeps alignment texture, drops leg/clutter) so background can't fuse into the mesh. | 32
M1 | W2 | KIRI reconstruction integration | Submit → webhook (signed) + poll fallback → fetch within link window; retries + credit metering. | 24
M1 | W2 | Mesh cleanup + watertight repair | Vertex merge, largest-component isolation, hole repair (pymeshfix) before any ray casting. | 16
M1 | W2 | Scale calibration (marker / LiDAR) | Reference-marker → mm/px, or LiDAR metric units. The one error nothing downstream can catch. | 24
M1 | W2 | Orientation (leg crop + stable-pose) | Crop the leg at the ankle, physics stable-pose to rest the sole on a floor; adaptive fallback. | 24
M1 | W2 | Measurement + validation + reliability flags | Length/width from footprint; arch by multi-slice ray casting; validate vs ground truth; flag implausible values. | 32
M1 | W3 | Standardized renders | Deterministic camera poses + dimensioned overlays, headless. | 16
M1 | W3 | Vision-LLM biomechanics (Agent 2) | Arch type, pronation/supination, estimated weight distribution → structured output. | 16
M1 | W3 | LangGraph orchestration | Typed shared state, checkpointing, resumable runs, clinician review interrupt, audit trail. | 24
M1 | W3 | Automated report — baseline (Agent 3) | Structured podiatry report (measurements + confidence + assessment + imagery). | 16
M1 | W3 | Clinician web app | Intake, live progress, review/approve-edit, results + reliability flags + report view. | 32
M1 | W3 | End-to-end + accuracy validation | Full run on real captures; validate against ground truth at the ±1 mm benchmark. | 16
Milestone 2 — Refinement & Improvement (2 weeks)
M2 | W4 | Parametric insole (.stl) generation (Agent 4) | Parametric CAD from measurements + prescription → manufacturable 3D-printable STL + manifest. | 32
M2 | W4 | Foot-only segmentation upgrade | Prompted/trained foot segmenter so the leg never enters reconstruction (fixes width on cluttered captures). | 24
M2 | W4 | Arch + measurement hardening | Multi-scan/multi-slice averaging, arch refinement, medial/lateral robustness; tighten reliability thresholds. | 24
M2 | W5 | Clinical validation set | Validate against additional ground-truth feet; publish per-measurement accuracy report. | 16
M2 | W5 | Errors, retries, edge cases | Reconstruction failures, timeouts, missed webhooks, bad captures; graceful degradation. | 16
M2 | W5 | Report polish (PDF) + manifest | Professional PDF report; manufacturing spec/manifest export. | 16
M2 | W5 | Observability + cost + deploy hardening | Per-node metrics, error tracking, KIRI/LLM cost dashboards; deployment + data-security/compliance. | 24
|  | Milestone 1 total (3 weeks) · hours |  | 336
|  | Milestone 2 total (2 weeks) · hours |  | 152
|  | TOTAL (5 weeks) · hours |  | 488
Achievable accuracy (with the mandated capture protocol)
Aspect | Outcome
Foot length / width | ±1–2 mm, validated at the ±1 mm clinical benchmark
Arch height | Reliable from weight-bearing capture
Scale | Metric (reference marker or LiDAR)
Insole output | Manufacturable 3D-printable .stl (end of Milestone 2)
Trust | Reliability flags on every measurement; implausible values are flagged, never shipped
Note | Accuracy depends on capture quality. The capture protocol (weight-bearing, foot-framed, scale marker/LiDAR, coverage) is a prerequisite, enforced by the quality gate.